## Slide 1: Suicide Prevention AMP Stand-up Discussion
April 25th, 2023

## Slide 2: Agenda
Topics | Objectives
Current Pilot Portfolios and Timeframe for Next AMP Stand-ups | Current Prototype Portfolios AMP stand-up timeline in ISRM
Steps to Stand Up a New Portfolio | Assessment Workplan Document and Processes Production
Meeting Objective
To align on timeframe and key tasks for standing up a new portfolio

## Slide 3: ISRM Pilot Portfolios
Leadership Model
Funding Model
Review Process
Clinical Science
R & D
D
Health Systems Broad Portfolio
Launch Date
Clinical Science
R & D
D
Behavioral/Mental Health Broad Portfolio
Director-led Model
Defined Budget
Standard Merit Review
1/31/2023
Single Senior PM Model
Competitive Budget
Accelerated + Standard Merit Review
6/1/2023
ISRM’s 4 Pilot Portfolios will test out different leadership, funding, and review models
Clinical Science
R & D
D
Pain / Opioid Use AMP
Clinical Science
R & D
D
Precision Oncology AMP
Single Senior PM Model
Accelerated + Standard Merit Review
11/1/2022
Rotational Model of 4 Scientific PMs
Competitive Budget
Standard Merit Review
1/31/2023
Defined Budget

## Slide 4: ISRM Pilot Portfolio Data and Expected New AMP Stand-ups
Data Expected
Clinical Science
R & D
D
Health Systems Broad Portfolio
Oct 1, 2023
Clinical Science
R & D
D
Behavioral/Mental Health Broad Portfolio
April 1, 2024
ISRM’s 4 Pilot Portfolios will provide full data for analysis ~ April 2024
Clinical Science
R & D
D
Pain / Opioid Use AMP
April 1, 2024
Clinical Science
R & D
D
Precision Oncology AMP
Sep 1, 2023
Expected timeframe for new AMP stand-ups is 2024 – after testing pilot portfolios and analyzing data

## Slide 5: What does it mean to fully stand-up a new portfolio?
3 Basic Steps to Stand up a New Portfolio
Estimated Time: 7 Months
Month 1
  Assess rationale for new portfolio
  Develop workplan to include meetings and production of documents and processes
    Meetings may include:
      CRADO
      ISRM Leadership (Cadence TBD)
      HR (Cadence TBD)
      Finance (Cadence TBD)
      Regulatory Review – IACUC, IRB
      Work Groups (Cadence TBD)
      Executive Committee (Cadence TBD)

## Slide 6: What does it mean to fully stand-up a new portfolio?
3 Basic Steps to Stand up a New Portfolio
Estimated Time: 7 Months
Months 2-7
3. Produce Documents and Processes

## Slide 7: Questions
Thank You
Questions?