## Slide 1: Suicide Prevention AMP Stand-Up
June 27th, 2023

## Slide 2: Agenda
Topics | Objectives
High-Level Overview of Portfolio Stand-ups | Present Advisory Group with the Portfolio stand-up process
AMP Stand-Up Next Steps | Discuss next steps involved in Suicide Prevention stand-up
Suicide Prevention Documentation – In Progress | Review draft documents for AMP stand-up

## Slide 3
High Level Overview

## Slide 4: Portfolio Stand-Ups
Our team has been working with ISRM leadership to develop and standardize a process for portfolio stand-ups. As this is a new process, our tools and templates are still in development, so they can serve as a resource to your team, but is not meant to be prescriptive in any way.
In this diagram below, you will see Stages 1-3. Suicide Prevention is already a portfolio in development and will not need the approval to engage in the stand-up process, thus bypassing “Stage 1”.
Stage 1
Stage 2
Stage 3
15 Days
15 Days
180 Days
New Portfolio Assessment
New Portfolio Execution
New Portfolio Planning
Step 1.1: Ensure you have a good understanding of the foundational documentation.
Step 1.2: Complete the New Portfolio Assessment Form.
Step 1.3: Connect with ISRM leadership and receive approval to begin Stage 2.
Step 2.1: Determine the required documents, processes, and meeting cadences needed to launch the new portfolio.
Step 2.2: Build a detailed workplan for the execution of the new portfolio.
Step 2.3: Connect with ISRM leadership to and receive approval to begin Stage 3.
Step 3.1: Complete charters and HR documents.
Step 3.2: Define purview and research priorities.
Step 3.3: Produce RFAs, SOPs, and Policies.
Step 3.4: Define data management and performance metrics.
Step 3.5: Publish RFAs and begin portfolio operations.

## Slide 5: Suicide Prevention is kicking off their development at Stage 2
Step 2.1
Step 2.2
Step 2.3
New Portfolio Workplanning
Use templates to create a comprehensive workplan for drafting required materials and establishing recurring meeting cadences for the development of the new portfolio.
Required Documents and Materials
Meet with ISRM Leadership to discuss materials and meetings checklist. Determine what materials and meeting cadences are required for the new portfolio.
Workplanning
Workplan Approval and Initiation
Once you have completed the comprehensive workplan, meet with ISRM leadership to review the plan and receive approval to move to Stage 3.

## Slide 6: This team hopes to arrive at Stage 3 by our next monthly meeting
New Portfolio Execution
Step 3.1
Step 3.2
Step 3.3
Step 3.4
Step 3.5
Charter and HR Documents
Purview and Research Priorities
RFAs, SOPs, and Policies
Data Management and Performance Metrics
Portfolio Operations
Use the templates and examples to draft the Charters and HR Documents required for the new portfolio.
Use the templates and examples to draft your Research Purview and define the Critical Research Priorities of the new portfolio.
Use the templates and examples to draft the RFAs, SOPs and Policies which will be foundational to the new portfolio.
Use the templates and examples to draft the Data Management Policies and determine the Performance Metrics of the new portfolio.
Finalize and publish the RFAs for the new portfolio and officially begin portfolio operations!

## Slide 7: Process Overview Timeline
Please Note: Timelines for the completion of stages and portfolio materials are recommendations
This is not a formalized stage 1, but SP is being built as an AMP so this stage can be bypassed
Present – July 31: Complete planning stages and begin portfolio document development
August 2023 – April 2024: Complete portfolio documentation and stand-up activities, including receiving approval from Leadership Council on all documentation

## Slide 8
AMP Stand-Up Next Steps

## Slide 9
Overview of Next Steps
By June 30th | Determine core workgroup for Suicide Prevention Stand-up Establish working cadence
By July 14th | Meet with ISRM Leadership to validate required documents Assign document ownership to workgroup members
By July 28th | Develop timeline to complete required documents Submit timeline to ISRM Leadership Report workplan to Suicide Prevention Advisory Group (July 25th
Notes: Clarify what we discussed with them today. Then bring in here is our recommende next

## Slide 10: Developing a Workplan
The Suicide Prevention workgroup will be populating a workplan that looks like this for ISRM leadership review. Upon its review and approval, the workgroup will bring this to the next Suicide Prevention Advisory Group Monthly Meeting in late July.
Sample Workplan

## Slide 11
Suicide Prevention AMP Documentation

## Slide 12
Suicide Prevention AMP Charter

## Slide 13
Purpose |  | Governance |  | 
The Suicide Prevention AMP is established to guide, direct, and manage the suicide prevention research portfolio for the Department of Veterans Affairs. The AMP is designed to be capable of developing research opportunities that are designed to answer specific real-world questions that are important to Veterans, providers, and/or the healthcare system by focusing on communication, coordination and collaboration between researchers, clinical partners, and other key stakeholders that promote and foster a team-based approach to research. | To answer real-world questions that are important to patients, providers, and/or the healthcare system by focusing on communication, coordination and collaboration between researchers, clinical partners, and other key stakeholders that promote team-based research opportunities **specify Veteran health | Structure: Executive Steering Committee Appointed Subcommittees Charters | Membership: VA Researchers VHA Clinical Partners VHA Leadership Federal Partners | Frequency: Monthly – Quarterly
Key Collaborators | Requirements | Supporting Capabilities | Supporting Capabilities | 
Within ORD: PMs managing behavioral health research Other research portfolios Research Operations Within VA: VHA Clinical Programs Operations partners/offices VHA Leadership Critical VHA partners (e.g., IT) External: Academic Affiliates Federal Partners Philanthropic and Professional Societies Industry partners | Strategically identify and fund research that seeks to answer specific, real-world questions that are important to Veterans, providers, and/or the healthcare system that results in the improvement of health, care and well-being of Veterans. Continue to support and encourage investigator-initiated suicide prevention research. Ensure that investigators are aware of needs of clinical operation partners and that clinical operations and external partners are aware of VA research products. Ensure that scientific research discoveries within the portfolio translate into clinical practice and inform healthcare decision making. Develop and implement quality improvement interventions that enhance research outcomes and support the achievement of the portfolio’s goals. Promote the continued maturation of VHA as a learning healthcare system through continued communication, coordination and collaboration with key stakeholders. |  | X Promoting team research and interdisciplinary collaboration Actively identifying related areas of research and connecting researchers Actively promoting/disseminating the outputs of research to ORD investigators Fostering development of early investigators X The ability to partner directly with appropriate program offices and/or clinical operations partners Fostering trust and cooperation between researchers and clinicians to promote team science Creating communities around conditions of interest that generate priority research opportunities Identifying and disseminating evidence of VA research with external organizations and supporting implementation of new evidence to inform guideline X Ability for AMP Leaders to rapidly identify and understand what research is currently taking place across the portfolio Ability to integrate data across the VA to facilitate greater coordination of multi-site trials Ability to support the development and use of common data elements across all research projects in the portfolio X Assessing portfolio composition to identify knowledge gaps in existing portfolio research Assessing how research in a portfolio is impacting clinical care The ability to analyze the maturity of the science Focusing on program directed research while continuing to foster the development of investigator-initiated projects Encouraging the reporting of measurements/outputs of research projects to inform leadership decision making and hold investigators accountable X The ability to independently direct funding opportunities Expedited review for program priority projects The ability to use other IRB’s Ensure high quality scientific peer review | 
 | Key Capabilities (with Supporting Capabilities) |  |  | 
 | Set research roadmap and strategic priorities​ Assessing portfolio composition to identify knowledge gaps in existing portfolio research Assessing how research in a portfolio is impacting clinical practice Analyzing the maturity of the science and respond to emerging areas Focusing on program directed research while continuing to foster the development of investigator-initiated projects Encouraging the reporting of measurements/outputs of research projects to inform leadership decision making and hold investigators accountable Rapidly review and fund prioritized research studies The ability to independently direct funding opportunities Expedited review for program priority projects Ensure high quality scientific peer review Foster greater collaboration between ORD research and VHA clinical partners as well as external collaborators The ability to partner directly with appropriate program offices and/or clinical operations partners Fostering trust and cooperation between researchers and clinicians to promote team science and provide opportunities for leadership Creating communities around diseases/conditions of interest that generate priority research opportunities Identifying and disseminating evidence of VA research internally and with external organizations and supporting implementation of new evidence to inform guideline Enable strategic coordination of research projects within the portfolio Promoting team research and interdisciplinary collaboration Actively identifying related areas of research and connecting researchers Actively promoting/disseminating the outputs of research to ORD investigators and the research community Fostering development and retention of early investigators Assisting in development of a Suicide Prevention Clinical Trial network capable to speed roll-out of large clinical trials. Enhance utilization of existing data and analytical tools to increase coordination and collaboration of research Ability for SP AMP Leader to rapidly identify and understand what research is currently taking place across the portfolio Ability to integrate data across the VA to facilitate greater coordination of multi-site trials/translational research studies Ability to support the development and use of common data elements to support data interoperability and interchange between stakeholders in the area of research |  |  | 

## Slide 14
Suicide Prevention AMP Leader Role Charter

## Slide 15
Purpose of the role |  |  | Series / Grade: Title: AMP Leader Location: Supervisory: Yes | Series / Grade: 15 Title: AMP Leader Location: Supervisory: Yes
The Suicide Prevention AMP lead oversees and coordinates the development of strategic priorities for the Suicide Prevention AMP by: 1. Developing communities of science consisting of researchers, clinicians, administrators, and Veterans who will set priorities for the portfolio 2. Promoting portfolio diversity and project opportunities within Suicide Prevention AMP 3. Partnering with VHA clinicians and sister agencies (e.g., NIH, DoD, etc.) to champion the benefits of ORD research with key stakeholders; and 4. Serving as an SME and POC for the Suicide Prevention AMP who will advise CRADO and senior leadership on the portfolio and issues related to the Suicide Prevention AMP. |  |  | Series / Grade: Title: AMP Leader Location: Supervisory: Yes | 
Organizational structure | Key Leadership Behaviors |  | Key Leadership Behaviors (if applicable) | 
 | Executing the strategic plan for Suicide Prevention AMP Coordinating with executive council on AMP portfolio development and strategic priorities Allocating and obligating AMP directed funds to achieve portfolio goals Overseeing the collection of critical measures for Suicide Prevention research projects Communicating the impact and successes of SP AMP approach and SP AMP research to key stakeholders Identify and promote the development of enterprise-wide resources based on Suicide Prevention AMP projects that can be utilized by the entire field Engage with other agencies on their priorities and research to enable cooperative opportunities Ensure portfolio support for the translation of therapies and treatments Develop relationships with key stakeholders to ensure breadth of portfolio addresses knowledge and practice gaps |  | High degree of leadership and comfort managing group dynamics Adept at balancing priorities and cross-cutting research projects Be an informed leader who understands the breadth of work being done in the topic area and within the portfolio while maintaining a research outlook beyond the immediate future Proficiency communicating to both scientific and lay audiences Engaged with other agencies on their priorities and research to enable cooperative opportunities Willing to assist research teams in generating alternative approaches to enable more collaborative and synergistic research efforts | 
Individual accountabilities |  |  |  | 
For all Actively Managed Portfolio Leaders |  |  | Specifics will vary depending on focus of the Actively Managed Portfolio | 
Develop relationships with investigators and other stakeholders across VAMCs/VISNs as well as with external groups Convene workshops and conferences that generate new ideas and collaborative opportunities Maintain adherence to data standards/procedures for all projects within the portfolio Ensure portfolio performance against agreed upon performance measures Hold investigators/sites accountable when performance measures/project milestones aren’t being met Ensure portfolio support for the translation of therapies and treatments Conduct regular and off-cycle reviews Review recurring portfolio analysis reports and provide recommendations to address gaps |  |  | Execute the strategic plan for SP AMP Coordinate with oversight group(s) on SP AMP portfolio development and strategic priorities Allocate and obligate SP AMP directed funds to achieve portfolio goals Oversee the collection of SP AMP project reports/measurements Communicate the impact and successes of SP AMP approach and SP AMP research to key stakeholders Identify and promote the development of enterprise-wide resources based on SP AMP projects that can be utilized by the entire field | ORD Finance Office, CRADO(Leadership Team), AO Relevant VHA Program Leadership, QUERI, interagency partners DEAN, OCLA, OPIA, OGC, VHA Communications, ORD Ops Director Investigator, Research Office, Office of Technology Transfer
Key Collaboration Network |  |  |  | 
Key shared accountabilities |  | Mission-critical collaborators | Mission-critical collaborators | 
Set SP AMP annual budget and determine resource allocation Guide implementation of research outputs into clinical care, clinical practice guidelines Share communications with clinical partners, clinical services and other partners Oversee strategic planning and implementation |  | ORD Finance Office, CRADO (Leadership Team), ISRM LEADERSHIP Relevant VHA Program Leadership, QUERI, interagency partners DEAN, OCLA, OPIA, OGC, VHA Communications, ORD Ops Director Investigator, Research Office, Office of Technology Transfer |  | 
SEE PROPOSED STRUCTURE IN SLIDES BELOW

## Slide 16
ISRM Organization

## Slide 17: Proposed Personnel Organization
AR&PM (SPMs)
6 Focus Areas
AR&PM (SPMs)
6 Focus Areas
QUERI
AR&PM (SPMs)
10 Focus Areas
Director, Suicide Prevention
Director, TBI
Director, MERP
Special Assistant
Scientific Portfolio Managers (SPMs) organized within broad portfolio
Separate administrative support for Application Review (AR) & Project Management (PM)
The Director of Research Integration (Deputy Director Later Takes This Role) acts as a conduit between AMPs and the Broad Portfolios
Deputy Director, ISRM
(7/24)
Director, Pain/OUD
Executive Director, Brain, Behavioral & Mental Health
Executive Director, Health System Improvement
Executive Director Functional Repair, Restoration & Replacement
Executive Director, Medical Health and Aging
Director, Precision Oncology
AR&PM (SPMs)
13 Focus Areas
DCRADO ISRM
ISRM Budget Management
HR Management
SOPs/Quality Management/ Records Management
Application Review Support
Project Management Support
Workforce Development
Clinical Trials Support
Director , ISRM Administration
Director of Research Integration
(Interim: 12/2023 – 7/2024)
Broad
Portfolios
Focused Portfolios (AMPs)
Support Services
Key
Leadership Group
Research Integration
SP EXECUTIVE COMMITTEE
Notes: Speaker Notes:
After much deliberation, we decided to move forward with this organizational structure. The AMPs will be reporting to the Broad Portfolios, and a centralized administrative unit will provide support across all portfolios, which we will discuss on the coming slides. Along with this structure came the updates of a few New Positions:
Director of ISRM Administration
  ISRM will have a director leading a centralized administrative unit to provide support across all portfolios
  This position will ensure alignment with the OWC Director of Operations and Director of Finance, along with adherence to ORD HR and Finance policies and procedures.
  Note: this administrative unit is a repurposing of administrative support previously in the services. While the Director is a new position, the units below it are drawn from preexisting positions.
Director of Research Integration
  ISRM will have an interim director position focused on the establishment of integration processes across all portfolios
Deputy Director
  A full-time Deputy Director will be hired and will replace and take on the responsibilities of the Interim Director of Research Integration as well as help oversee the entire organization.

## Slide 18
DCRADO ISRM
Staff Salaries Administration
Brain, B/M Health
Focus Areas
Medical Health and Aging
Focus Areas
Functional RRR
Focus Areas
Health Systems
Focus Areas
QUERI
Suicide Prevention
TBI
Precision Oncology
MERP
Pain/OUD
Other Focused Portfolios
Under the “service” structure, there were fewer “buckets” of funding, which decreased our ability to ensure faithful execution of Congressional commitments. For example, if we committed to increase investments in precision oncology, it required continual tracking across four services. The new structure would enhance our ability to closely track expenditures associated with high visibility portfolios of research, such as traumatic brain injury and military exposures.
18
Proposed Funding Model
Broad
Portfolios
Focused Portfolios
Support Services
Key
Leadership Group
ISRM Leadership Council
Notes: Speaker Notes:
Under the current “service” structure, there were fewer “buckets” of funding, which decreased our ability to ensure faithful execution of Congressional commitments. For example, if we committed to increase investments in precision oncology, it required continual tracking across four services.
With this new portfolio structure, we would enhance our ability to closely track expenditures associated with high visibility portfolios of research, such as traumatic brain injury and military exposures.

## Slide 19: Proposed Functional Matrix
Investigators, Scientific Review Management (ISRM) Leadership Council
Administrative Support Services
Military Exposures Research Program
Traumatic Brain Injury
Suicide Prevention
Pain/Opioid Use Disorder
Precision Oncology
Brain, Behavioral & Mental Health
Medical Health and Aging
Functional Repair, Restoration, & Replacement
Health Systems
Other Focused Research
A matrixed organizational model will promote cross-portfolio integration of research
Broad
Portfolios
Focused Portfolios (AMPs)
Support Services
Key
Leadership Group
Notes: Speaker Notes:
ISRM will become a matrixed organization across multiple dimensions
While the broad portfolios and actively managed portfolios will matrix across each other in addressing research initiatives, the administrative support services will work across all portfolios to provide key support. We believe that this placement of services will allow for more equitable access and allocation of these resources for the research teams.

## Slide 20: Integration at the junctions between Broad Portfolios and Focused Portfolios (AMPs)
Integration Junction
SPMs in the broad portfolios work in a team with the AMP Director
SPMs in the broad portfolios review applications submitted to the AMP RFAs
SPMs in the broad portfolios manage funded projects with the AMP Directors
AMPs have independent budgets and AMP Directors conduct funding recommendation meetings with relevant SPMs
Focused Portfolio (AMP)
Staff:
Senior Portfolio Manager
Broad Portfolio
Staff:
Directors
SPMs of the discipline area
Notes: Speaker Notes:
At each intersection between the broad portfolios and actively managed portfolios, operational activities overlap.
The broad portfolios contain directors and SPMs of the discipline area while the Focused Portfolios (AMPs) contain Senior Portfolio Managers. At the integration junction:
SPMs in the broad portfolios work in a team with the AMP Director
SPMs in the broad portfolios review applications submitted to the AMP RFAs
SPMs in the broad portfolios manage funded projects with the AMP Directors
AMPs have independent budgets and AMP Directors conduct funding recommendation meetings with relevant SPMs

## Slide 21: Proposed New Application Review and Project Management Process
Each Portfolio develops and publishes RFAs
Investigators submit applications through the RFA requesting peer-review by SMRB of their choice
SRG convenes and reviews/scores the application
The score/reviews go to a funding meeting convened by the Portfolio which had posted the RFA through which the application had been submitted.
A prioritized list is developed at the portfolio funding meeting which is submitted to the ISRM Leadership Council for approval.
Funded applications are returned to the SPM who managed the review to oversee JIT approvals and the conduct of the research working with the leadership of the portfolio which funded the project.
Step-by-Step Process
SRG 1
SRG 3
Portfolio A Specific RFA
Portfolio B Specific RFA
Portfolio C Specific RFA
SRG 4
Portfolio B Funding Meeting
Portfolio C Funding Meeting
SRG 1
SPM
SRG 2
SPM
SRG 3
SPM
SRG 4
SPM
…
…
…
…
…
Application 3
Application 1
SRG 2
Portfolio A Funding Meeting
Application 2